## Projectplanning
Project | ID | WP | Category | Type | Description & Link | Start date | End date | Status | Partner | Remark | Report
CLAM | T142 | WP3 |  | Software | CLAM is software to build webservices and webapplication and is used by many NLP webservices in and beyond of CLARIN/CLARIAH | Q1 2019 | Q4 2023 | In progress | KNAW | This is an ongoing support and development task. Support is being offered to the developers of the services | Task plan
| T142D1 | WP3 | Deliverable | Software | CLAM | 2010 |  | Active | KNAW
| T142D1.1 | WP3 | Deliverable | Documentation | Documentation | 2010 |  | Active | KNAW
| T142M1 | WP3 | Milestone | Software | CLAM v3.0 |  | Q4 2019 | Complete | KNAW
FoLiA | T108 | WP3 |  | Software | FoLiA is a format for linguistic annotation that is being used throughout CLARIAH, by both tools and data sets, and is an important facility to maintain for the future | Q1 2019 | Q4 2023 | In progress | KNAW | This is an ongoing support and development task | Task plan | Milestone
| T108D1 | WP3 | Deliverable | Documentation | FoLiA Documentation and Reference Guide | 2011 |  | Active | KNAW
| T108D2 | WP3 | Deliverable | Data | FoLiA Schemas and Specification | 2010 |  | Active | KNAW
| T108D3 | WP3 | Deliverable | Software | FoLiA Library for Python: FoLiAPy | 2010 |  | Active | KNAW
| T108D4 | WP3 | Deliverable | Software | FoLiA Library for C++: libfolia | 2011 |  | Active | KNAW
| T108D5 | WP3 | Deliverable | Software | FoLiA Library for Rust: folia-rust | Q2 2019 |  | Active | KNAW | Experimental
| T108D6 | WP3 | Deliverable | Software | FoLiA Tools (Assorted command-line tools for FoLiA, Python-based) | 2011 |  | Active | KNAW
| T108D7 | WP3 | Deliverable | Software | FoLiA Utilities (Assorted command-line tools for FoLiA, C++) | 2013 |  | Active | KNAW
| T108D8 | WP3 | Deliverable | Software | FoLiA profiler for CLARIN Switchboard/weblicht | Q2 2020 |  | Active | KNAW
| T108D9 | WP3 | Deliverable | Software | Piereling Webservice - A webservice to convert various document formats from/to FoLiA. Builds upon foliatools and foliautils. | Q3 2019 |  | Active | KNAW
| T108D10 | WP3 | Deliverable | Service | Piereling Webservice deployed at CLST. | Q3 2019 |  | Active | RUN
| T108M1 | WP3 | Milestone | Data | FoLiA v2.0 | Q3 2018 | Q1 2019 | Complete | KNAW
| T108M2 | WP3 | Milestone | Data | FoLiA v3.0 | ? | ? | Not started | KNAW | This is a hypothetical future milestone that would propose changes to FoLiA for better alignment with the CLARIAH infrastructure; these tasks are not defined yet and need to arise from discussion (in e.g. the CLARIAH Interest Groups) and practical experience. Possible solutions could be a new serialisation form that integrates nicely into the world of lin…
FLAT | T062 | WP3 |  | Software/ Service | FLAT ensures FoLiA documents can be visualised and annotated by human annotators. | Q1 2019 | Q4 2023 | In progress | KNAW | Since 14 July 2020 - This task has moved from CLST, Radboud University Nijmegen to Digital Infrastructure, Humanities Cluster, KNAW. A FLAT installation and supported at CLST. • Merged this task with other FLAT tasks (T063,T064,Txx1,T096), the allocated PMs however only suffice for a subpart. I explicitly listed proposed enhancements that will probably not be implemented (unless priorities/funding changes) | Task plan | Deliverable
| T062D1 | WP3 | Deliverable | Software | FLAT | 2014 |  | Active | KNAW
| T062D1.1 | WP3 | Deliverable | Documentation | Administration Guide | 2016 |  | Active | KNAW
| T062D1.2 | WP3 | Deliverable | Documentation | User Guide | 2016 |  | Active | KNAW
| T062D1.3 | WP3 | Deliverable | Documentation | Installation Guide | 2016 |  | Active | KNAW
| T062D2 | WP3 | Deliverable | Software | foliadocserve - The backend for FLAT | 2015 |  | Active | KNAW
| T062D3 | WP3 | Deliverable | Service | FLAT installation at CLST, Radboud University, Nijmegen | 2015 |  | Active | RUN
| T062M1 | WP3 | Milestone | Software | FLAT v0.9.0 | Q2 2019 | Q3 2019 | Complete | KNAW
Frog & DeepFrog | T139 | WP3 |  | Software | Frog is a widely popular and used tool in the Dutch NLP community, it’s support and maintenance must remain guaranteed in the future. | Q1 2019 | Q4 2023 | In Progress | KNAW | This task has entered a new stage and has been revised now lead developer Ko van der Sloot has retired. Almost all of the earlier deliverables have been completed and further maintenaince is now guaranteed by Maarten van Gompel. | Task plan
Frog | T139aD1 | WP3 | Deliverable | Software | Frog | 2011 |  | Active | KNAW
| T139aD1.1 | WP3 | Deliverable | Documentation | Frog Documentation | 2018 |  | Active | KNAW
| T139aD1.2 | WP3 | Deliverable | Data | Frogdata – Trained models for Frog | 2012 |  | Active | KNAW
| T139aD1.3 | WP3 | Deliverable | Software | Python-frog: Python binding for Frog | 2014 |  | Active | KNAW
| T139aD1.4 | WP3 | Deliverable | Software | Frog Webservice | 2012 |  | Active | KNAW
| T139aM1 |  | Milestone | Software | Frog v0.20 | Q4 2019 | Q1 2020 | Complete | KNAW | Due to the support character of this task, no further Frog milestones are planned in advance. New releases will be done as bugs emerge and are fixed |  | Complete
| T139aD2 | WP3 | Deliverable | Software | Ucto | 2011 |  | Active | KNAW
| T139aD2.1 | WP3 | Deliverable | Documentation | Ucto Documentation | 2018 |  | Active | KNAW
| T139aD2.2 | WP3 | Deliverable | Data | Rule-based configurations for ucto for various languages | 2016 |  | Active | KNAW
| T139aD2.3 | WP3 | Deliverable | Software | Python-ucto: Python-binding for ucto | 2014 |  | Active | KNAW
| T139aD2.4 | WP3 | Deliverable | Software | Ucto Webservice | 2012 |  | Active | KNAW
| T139aD3 | WP3 | Deliverable | Service | Frog webservice deployed at CLST | 2012 |  | Active | RUN
| T139aD4 | WP3 | Deliverable | Service | Ucto webservice deployed at CLST | 2012 |  | Active | RUN
DeepFrog | T139bD1 | WP3 | Deliverable | Software | Deepfrog | Q1 2020 | (Q3 2020) | Suspended | KNAW | Jan 2021: The DeepFrog task is on hold since Q3 2020 as there seems to be no official budget/time for it and other priorities have taken precendence.
| T139bD1.1 | WP3 | Deliverable | Documentation | Deepfrog documentation | ? | ? | Not started | KNAW | idem
| T139bD1.2 | WP3 | Deliverable | Software | Training pipelines for training the models | Q1 2020 |  | Suspended | KNAW | idem
| T139bD1.3 | WP3 | Deliverable | Software | DeepFrog webservice | ? | ? | Not started | KNAW | idem
| T139bD2 | WP3 | Deliverable | Data | Models for PoS, NER, lemmatisation for Dutch | Q1 2020 |  | Suspended | KNAW | idem
| T139bD3 | WP3 | Deliverable | Paper | Deepfrog paper describing the new models and comparing them with the current Frog | ? | ? | Not started | KNAW | idem
DeepFrog | T139bM1 | WP3 | Milestone |  | Exploration stage towards finding possible solutions for each of the components | Q1 2020 | ? | Complete | KNAW |  |  | In progress
DeepFrog | T139bM2 | WP3 | Milestone | Software | Implementation stage | Q2 2020 | ? | On hold | KNAW | Delivered a first experimental version of DeepFrog |  | Not started
DeepFrog | T139bM3 | WP3 | Milestone |  | Evaluation stage | ? | ? | On hold | KNAW |  |  | On hold
DeepFrog | T139bM4 | WP3 | Milestone |  | Revision stage | ? | ? | On hold | KNAW
LaMachine | T098 | WP3 |  | Software | LaMachine is the umbrella under which we make available a lot of our software. This task is a support and maintenance task | Q1 2019 | Q4 2023 | In progress | KNAW | Increased estimated PM from 6 to 9 (the officially allocated 3PM is very insufficient!) • Since 14 July 2020 - This task has moved from CLST, Radboud University Nijmegen to Digital Infrastructure, Humanities A comprehensive LaMachine intallation hosting various webservices is retained and supported at CLST. | Task plan | WP2
LaMachine | T098D1 | WP3 | Deliverable | Software | LaMachine | 2015 |  | Active | KNAW |  |  | WP3
| T098D1.1 | WP3 | Deliverable | Documentation | LaMachine | 2015 |  | Active | KNAW
| T098D1.2 | WP3 | Deliverable | Website | LaMachine website | 2015 |  | Active | KNAW
| T098D1.3 | WP3 | Deliverable | Software Image | Docker hub image with a default subset of software | 2018 |  | Active | KNAW
| T098D1.4 | WP3 | Deliverable | Software Image | Vagrant/Virtualbox image with a default subset of software | 2018 |  | Active | KNAW
Labirinto | T098D2 | WP3 | Deliverable | Software | Labirinto: Powers the portal website inside LaMachine | 2018 |  | Active | KNAW |  |  | WP4
LaMachine Homebrew Recipes | T098D3 | WP3 | Deliverable | Software | Recipes for Frog and dependencies for Homebrew: LaMachine Homebrew recipes | 2018 |  | Active | KNAW |  |  | WP5
CodemetaPy | T098D4 | WP3 | Deliverable | Software | Codemetapy: A tool to convert software metadata between different formats, used by LaMachine. This is our contribution to the codemeta project | 2018 |  | Active | KNAW |  |  | WP6
LaMachine deployment | T098D5 | WP3 | Deliverable | Service | LaMachine Deployment at CLST, hosting a wide variety of services | 2015 |  | Active | RUN
Lamastats | T098D6 | WP3 | Deliverable | Software | Simple usage statistics for services included in LaMachine, through log analysis | 2016 |  | Active | KNAW
Testing Milestone - LaMachine#182 - | T098M1 | WP3 | Milestone | Software | Integration of webservice/webapp testing/monitoring facilities | ? | ? | Not started | KNAW | postponed in favour of other priorities
Authentication Milestone - LaMachine#171 - | T098M2 | WP3 | Milestone | Software | Integration of a CLARIN-compatible authentication solution | Q1 2021 | Q2 2021 | In progress | KNAW
Virtual Research Environment (VRE) | T137 | WP3 |  | Service | Development and coordination of the WP3 Virtual Research Environment | Q4 2020 | ? | In progress | KNAW | This is a development and coordination task | Task plan
VRE | T137D1 | WP3 | Deliverable | Service | Deploy a LaMachine installation that is preconfigured for maximum Interoperability between various WP3 services. This can be an Extension of the current installation at CLST or a new one at HuC. | Q3 2020 | Q3 2021 | In progress | KNAW
| T137D2 | WP3 | Deliverable | Documentation | Provide documentation for end-users, preferably and at least in the form of screencast videos demonstrating various user stories. | Q2 2021 | Q3 2021? | Not started | KNAW | starts after completion of the most significant milestones
CLAM | T137M1 | WP3 | Milestone | Software | CLAM v3.1 – Implement new connectivity features for CLAM as Proposed in the third CLARIAH WP3 VRE plan. |  | Q2 2021 | In progress | KNAW
FLAT | T137M2 | WP3 | Milestone | Software | FLAT v1.0 – Implement new features proposed in VRE plan |  | Q2 2021 | In progress | KNAW
LaMachine | T137M3 | WP3 | Milestone | Software | LaMachine v3.0 – Implement features proposed in VRE plan |  | Q2 2021 | In progress | KNAW
Switchboard Registry |  | WP3 | Deliverable | Data | Participation of our services in the CLARIN Switchboard Registry | Q1 2019 |  | Active | RUN/KNAW
clam2switchboard |  | WP3 | Deliverable | Software | Clam2switchboard - Software to help with conversion to switchboard registry | Q1 2019 |  | Active | KNAW
PICCL | ? |  |  | Software | [5 empty] | This task is not officially maintained by us, but was coordinated by Martin Reynaert. What happened to the CLARIAH-PLUS successor tasks that might continue on this (T012? managed by INT), is unclear to me.
Ticcltools |  |  | Deliverable | Software | Ticcltools |  |  | Inactive | UvT/RUN
PICCL |  |  | Deliverable | Software | PICCL |  |  | Inactive | RUN
Note on I1: Status for software deliverables uses the vocabulary from https://repostatus.org